## Splash
License: / This document, like most OpeningDesign's projects, is open source (Attribution-ShareAlike 4.0 International--CC BY-SA 4.0)--freely available to any party, for any use, assuming the terms such as Attribution and ShareAlike are honored.

## Hour Breakdown
Square Footage	17,000 SF
How Many Dwelling Units	17 units
Estimated Dollar per Square Footage	150 $/SF
Total Estimated Construction Costs	$2,550,000.00
Architecture Fees - Percentage of Construction	4.6%
Architecture Fees Only	$117,300.00
Architecture Fees – Cost per SF	6.9 $/SF
Architecture Fees – Cost per Unit	$6900/unit

Architecture & Eng Fees - Percentage of Construction	5.5%
Architecture & Engineering Fees	$140,250.00
Architecture & Engineering Fees – Cost per SF	8.3 $/SF
Architecture & Engineering Fees – Cost per Unit	$8250/unit

Man Hour Breakdown – Architecture Only
Average ($/Hr) Billing Rate	$80.00
		Each Phase	% of Construction	Cumulative	Cost per SF	Cost per SF Cumulative	Hours dedicated to each phase	Weeks – 1/10 person	Weeks – 1/8 person	Weeks – 1/5 person	Weeks – ¼ person	Weeks – 1/3 person	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1: / Pre-Design & Programming	10.00%	$11,730.00	0.46%	$11,730.00	$0.69	$0.69	147 hrs	36.7 wks	29.3 wks	18.3 wks	14.7 wks	11.3 wks	7.3 wks	4.9 wks	3.7 wks	2.4 wks	1.8 wks	1.5 wks	1.2 wks
Phase 2: / Schematic Design	15.00%	$17,595.00	0.69%	$29,325.00	$1.04	$1.73	220 hrs	55.0 wks	44.0 wks	27.5 wks	22.0 wks	16.9 wks	11.0 wks	7.3 wks	5.5 wks	3.7 wks	2.7 wks	2.2 wks	1.8 wks
Phase 3: / Design Development	20.00%	$23,460.00	0.92%	$52,785.00	$1.38	$3.11	293 hrs	73.3 wks	58.7 wks	36.7 wks	29.3 wks	22.6 wks	14.7 wks	9.8 wks	7.3 wks	4.9 wks	3.7 wks	2.9 wks	2.4 wks
Phase 4: / Construction Documents	30.00%	$35,190.00	1.38%	$87,975.00	$2.07	$5.18	440 hrs	110.0 wks	88.0 wks	55.0 wks	44.0 wks	33.8 wks	22.0 wks	14.7 wks	11.0 wks	7.3 wks	5.5 wks	4.4 wks	3.7 wks
Phase 5: / Bidding and Issuing for Permit	5.00%	$5,865.00	0.23%	$93,840.00	$0.35	$5.52	73 hrs	18.3 wks	14.7 wks	9.2 wks	7.3 wks	5.6 wks	3.7 wks	2.4 wks	1.8 wks	1.2 wks	0.9 wks	0.7 wks	0.6 wks
Phase 6: / Construction Administration	20.00%	$23,460.00	0.92%	$117,300.00	$1.38	$6.90	293 hrs	73.3 wks	58.7 wks	36.7 wks	29.3 wks	22.6 wks	14.7 wks	9.8 wks	7.3 wks	4.9 wks	3.7 wks	2.9 wks	2.4 wks
All Phases	100.00%	$117,300.00	4.60%	$117,300.00	$6.90	$6.90	1,466 hrs	366.6 wks	293.3 wks	183.3 wks	146.6 wks	112.8 wks	73.3 wks	48.9 wks	36.7 wks	24.4 wks	18.3 wks	14.7 wks	12.2 wks
All Phases						91.6 months	73.3 months	45.8 months	36.7 months	28.2 months	18.3 months	12.2 months	9.2 months	6.1 months	4.6 months	3.7 months	3.1 months
Phase 1-5 Only						293.3 wks	234.6 wks	146.6 wks	117.3 wks	90.2 wks	58.7 wks	39.1 wks	29.3 wks	19.6 wks	14.7 wks	11.7 wks	9.8 wks
Phase 1-5 Only						73.3 months	58.7 months	36.7 months	29.3 months	22.6 months	14.7 months	9.8 months	7.3 months	4.9 months	3.7 months	2.9 months	2.4 months

## Hourly Rates - Entire Team
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Overall Construction Costs	A Rough Estimated Percentage of Fees	Cost with Approach (A)	Cost with Approach (B)	Cost with Approach (C)	Cost per SF	Cost per Unit
Architecture – OpeningDesign				2.30%	42%	$58,650	$69,314	$79,977	3.5 $/SF	3,450 $/SF
Principal	$110/HR	$125/HR	$140/HR
Project Architect	$80/HR	$95/HR	$110/HR
Intern	$65/HR	$80/HR	$95/HR
Architecture – LKB Architecture				2.30%	42%	$58,650	$69,314	$79,977	3.5 $/SF	3,450 $/SF
Principal	$110/HR	$125/HR	$140/HR
Structural Engineer				0.90%	16%	$22,950	$27,123	$31,295	1.4 $/SF	1,350 $/SF
Engineer I	$260/HR	$275/HR	$290/HR
Senior Drafter	$80/HR	$95/HR	$110/HR
Junior Drafter	$65/HR	$80/HR	$95/HR
Civil Engineer				0.00%	0%	$0	$0	$0	.0 $/SF	$/SF
Engineer III	$135/HR	$150/HR	$165/HR
Engineer II	$120/HR	$135/HR	$150/HR
Engineer I	$105/HR	$120/HR	$135/HR
Robotic Crew	$130/HR	$145/HR	$160/HR
Professional Land Surveyor	$125/HR	$140/HR	$155/HR
Mechanical Engineer				0.00%	0%	$0	$0	$0	.0 $/SF	$/SF
Engineer III	$80/HR	$95/HR	$110/HR
Engineer II	$70/HR	$85/HR	$100/HR
Engineer I	$60/HR	$75/HR	$90/HR
Electrical Engineer				0.00%	0%	$0	$0	$0	.0 $/SF	$/SF
Engineer III	$150/HR	$165/HR	$180/HR
Engineer II	$100/HR	$115/HR	$130/HR
Engineer I	$90/HR	$105/HR	$120/HR
Plumbing Engineer				0.00%	0%	$0	$0	$0	.0 $/SF	$/SF
Engineer III	$80/HR	$95/HR	$110/HR
Engineer II	$70/HR	$85/HR	$100/HR
Engineer I	$60/HR	$75/HR	$90/HR
Lighting				0.00%	0%	$0	$0	$0	.0 $/SF	$/SF
Skill Level 1	$100/HR	$115/HR	$130/HR
Skill Level 2	$90/HR	$105/HR	$120/HR
Skill Level 3	$80/HR	$95/HR	$110/HR

Potential Additional Consultants				0.00%	0%	$0	$0	$0	.0 $/SF	$/SF
• Building Envelope Consultant
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				5.50%	100.00%	$140,250	$165,750	$191,250	8.3 $/SF	8,250.0 $/SF

## Hourly Rates - ARCH
Discipline	Approach / (A)	Approach / (B)	Approach / (C)
Architecture – OpeningDesign	0	0	0
Principal	$110/HR	$125/HR	$140/HR
Project Architect	$80/HR	$95/HR	$110/HR
Intern	$65/HR	$80/HR	$95/HR

## Hourly Rates - ARCH & STRUCT
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	Cost with Approach (A)	Cost with Approach (B)	Cost with Approach (C)
Architecture – OpeningDesign	0	0	0	42%	$58,650	$69,314	$79,977
Principal	$110/HR	$125/HR	$140/HR
Project Architect	$80/HR	$95/HR	$110/HR
Intern	$65/HR	$80/HR	$95/HR
Structural Engineer	0	0	0	16%	$22,950	$27,123	$31,295
Engineer I	$260/HR	$275/HR	$290/HR
Junior Drafter	$65/HR	$80/HR	$95/HR
Junior Drafter	$55/HR	$70/HR	$85/HR
Totals				58%	$81,600	$96,436	$111,273

## Increments
Increment Percentage	1.00%
Time Increment	1.1
Dollar Increments	15
Retainer Percentage	15.00%

## Fee Breakdown-$ & %
%	Phase	Approach (A)				Approach (B)				Approach (C)
		Rough % of Const. Costs	Estimated Duration	Not-To-Exceed		Rough % of Const. Costs	Estimated Duration	Not-To-Exceed		Rough % of Const. Costs	Estimated Duration	Not-To-Exceed
10.00%	Phase 1: / Pre-Design & Programming	0.6%	3.7 wks	$14,025		0.7%	4.8 wks	$16,575		0.8%	6.0 wks	$19,125
15.00%	Phase 2: / Schematic Design	0.8%	5.5 wks	$21,038		1.0%	7.1 wks	$24,863		1.1%	9.1 wks	$28,688
20.00%	Phase 3: / Design Development	1.1%	7.3 wks	$28,050	$25,245	1.3%	9.5 wks	$33,150		1.5%	12.1 wks	$38,250
30.00%	Phase 4: / Construction Documents	1.7%	11.0 wks	$42,075	$42,075	2.0%	14.3 wks	$49,725		2.3%	18.1 wks	$57,375
5.00%	Phase 5: / Bidding and Issuing for Permit	0.3%	1.8 wks	$7,013	$7,013	0.3%	2.4 wks	$8,288		0.4%	3.0 wks	$9,563
20.00%	Phase 6: / Construction Administration	1.1%	n/a	$28,050	$1,403	1.3%	n/a	$33,150		1.5%	n/a	$38,250
100.00%	All Phases	5.5%	29.3 wks	$140,250	$75,735	6.50%	38.1 wks	$165,750		7.50%	48.4 wks	$191,250
Retainer				$21,038				$24,863				$28,688
Assuming a Construction Cost, please see note below =											$2,550,000

## Fee Breakdown-%
%	Phase	Approach (A)				Approach (B)				Approach (C)
		Rough % of Const. Costs	Rough % of Overall Fee	Estimated Duration		Rough % of Const. Costs	Rough % of Overall Fee	Estimated Duration		Rough % of Const. Costs	Rough % of Overall Fee	Estimated Duration
10.00%	Phase 1: / Pre-Design & Programming	0.6%	10.0%	3.7 wks		0.7%	10.0%	4.8 wks		0.8%	10.0%	6.0 wks
15.00%	Phase 2: / Schematic Design	0.8%	15.0%	5.5 wks		1.0%	15.0%	7.1 wks		1.1%	15.0%	9.1 wks
20.00%	Phase 3: / Design Development	1.1%	20.0%	7.3 wks		1.3%	20.0%	9.5 wks		1.5%	20.0%	12.1 wks
30.00%	Phase 4: / Construction Documents	1.7%	30.0%	11.0 wks		2.0%	30.0%	14.3 wks		2.3%	30.0%	18.1 wks
5.00%	Phase 5: / Bidding and Issuing for Permit	0.3%	5.0%	1.8 wks		0.3%	5.0%	2.4 wks		0.4%	5.0%	3.0 wks
20.00%	Phase 6: / Construction Administration	1.1%	20.0%	n/a		1.3%	20.0%	n/a		1.5%	20.0%	n/a
100.00%	All Phases	5.5%	100.0%	29.3 wks		6.50%	100.0%	38.1 wks		7.50%	100.0%	48.4 wks

## Fee Breakdown-$
%	Phase	Approach (A)			Approach (B)			Approach (C)
		Not-To-Exceed	Estimated Duration		Not-To-Exceed	Estimated Duration		Not-To-Exceed	Estimated Duration
10.00%	Phase 1: / Pre-Design & Programming	$14,025	3.7 wks		$16,575	4.8 wks		$19,125	6.0 wks
15.00%	Phase 2: / Schematic Design	$21,038	5.5 wks		$24,863	7.1 wks		$28,688	9.1 wks
20.00%	Phase 3: / Design Development	$28,050	7.3 wks		$33,150	9.5 wks		$38,250	12.1 wks
30.00%	Phase 4: / Construction Documents	$42,075	11.0 wks		$49,725	14.3 wks		$57,375	18.1 wks
5.00%	Phase 5: / Bidding and Issuing for Permit	$7,013	1.8 wks		$8,288	2.4 wks		$9,563	3.0 wks
20.00%	Phase 6: / Construction Administration	$28,050	n/a		$33,150	n/a		$38,250	n/a
100.00%	All Phases	$140,250	29.3 wks		$165,750	38.1 wks		$191,250	48.4 wks

## Fees Per Disapline
Disciplines	Approach (A)		Approach (B)		Approach (C)
Architecture – OpeningDesign	2.30%	$58,650	2.72%	$69,314	3.14%	$79,977
Structural Engineer	0.9%	$22,950	1.06%	$27,123	1.23%	$31,295
Civil Engineer	0.0%	$0	0.00%	$0	0.00%	$0
Mechanical Engineer	0.0%	$0	0.00%	$0	0.00%	$0
Electrical Engineer	0.00%	$0	0.00%	$0	0.00%	$0
Plumbing Engineer	0.00%	$0	0.00%	$0	0.00%	$0
Lighting	0.00%	$0	0.00%	$0	0.00%	$0
Potential Additional Consultants	0.00%	$0	0.00%	$0	0.00%	$0
Totals	5.5%	$140,250	6.5%	$165,750	7.5%	$191,250

## Details
Start	$300
Number of Details	58
Increments	$20

	Cost Per Detail			Total
Approach A	$300	-	$320	$17,400	-	$18,560
Approach B	$340	-	$360	$19,720	-	$20,880
Approach C	$380	-	$400	$22,040	-	$23,200

## Sheet12
$1,300,000.00
4.67%	$60,710.00

Phase 1: / Pre-Design & Programming	10.00%	0.47%	$6,071.00
Phase 2: / Schematic Design	25.00%	1.17%	$15,177.50	$21,248.50	$14,000.00
Phase 3: / Design Development	20.00%	0.93%	$12,142.00	$33,390.50
Phase 4: / Construction Documents	20.00%	0.93%	$12,142.00	$45,532.50
Phase 5: / Bidding and Issuing for Permit	5.00%	0.23%	$3,035.50	$48,568.00
Phase 6: / Construction Administration	20.00%	0.93%	$12,142.00	$60,710.00
		4.67%	$60,710.00

229	$60.00	$13,740.00